## Requirements List
S. NO. | REQUIREMENTS | PRIORITY LEVEL
1 | Create an Income Tracker that stores all the incomes earned. | 1
2 | Create a Daily Expense Tracker that stores all the expenditures. | 1
3 | All transactions should be tagged back to the bank account. | 1
4 | All incomes/expenses should be categorised to 'Category' | 1
5 | A section for managing these Categories. | 1
6 | Deploy to Cloud. | 1
7 | Add a connection to automatically fetch the transactions from Google pay. | 2
8 | Add an option to download reports. | 2
9 | Dashboard to monitor incomes. | 2
10 | Dashboard to monitor expenses. | 2
11 | Add authentication to the system. | 3
12 | Add family system to allow multiple members under a single family. | 4
13 | Add Admin section to manage the entire family finances. | 5

## Tech Interpretation
Req. No. | Category | Solution | Task List
1 | DB | Create a schema - Income
|  | Add a table -Income | user id
income ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
category id
|  | Add a table - Bank Account | user id - pk
balance - dec
name of bank - char
account id
account no. - varchar
| Backend | Create CRUD for Income | Income - Create
Income - Read
Income - Update
Income - Delete
|  | Create CRUD for Bank Account | Bank account- Create
Bank account - Read
Bank account - Update
Bank account - Delete
2 | DB | Create a schema - expense
|  | Add a table -expense | user id
expense ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
category id
|  | Add a table - Bank Account | user id - pk
balance - dec
name of bank - char
account id
account no. - varchar
| Backend | Create CRUD for expense | expense - Create
expense - Read
expense - Update
expense - Delete
|  | Create CRUD for Bank Account | Bank account- Create
Bank account - Read
Bank account - Update
Bank account - Delete
3 | DB | Create a schema - transaction
|  | Add a table -Income | user id
income ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
category id
|  | Add a table - Bank Account | user id - pk
balance - dec
name of bank - char
account id
account no. - varchar
|  | Add a table -expense | user id
expense ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
category id
| Backend | Requirements from 1 and 2
4 | DB | Create a schema - category
|  | Add a table -Income | user id
income ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
category id
|  | Add a table - Bank Account | user id - pk
balance - dec
name of bank - char
account id
account no. - varchar
|  | Add a table -expense | user id
expense ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
|  | Add a table - category | user id
category id
category type - inc/exp
| Backend | Create CRUD for category | category - Create
category - Read
category - Update
category - Delete
5 | DB | Create a schema - category
|  | Add a table -Income | user id
income ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
category id
|  | Add a table - Bank Account | user id - pk
balance - dec
name of bank - char
account id
account no. - varchar
|  | Add a table -expense | user id
expense ID - int
income amt - dec
Date -dd/mm/yyyy
description - char
account id
|  | Add a table - category | user id
category id
category type - inc/exp
| Backend | same as 4th
6 | DB

## Task List
Task No. | Description | Time Needed
1 | postgres implementation of DB:
| income table | 3 hrs
| expense table | 3 hrs
| bank account table | 3 hrs
| category table | 3 hrs
2 | backend - api development
Expense
| create | 20 mins
| read | 20 mins
| update | 20 mins
| delete | 20 mins
Income
| create | 20 mins
| read | 20 mins
| update | 20 mins
| delete | 20 mins
bank account
| create | 20 mins
| read | 20 mins
| update | 20 mins
| delete | 20 mins
category
| create | 20 mins
| read | 20 mins
| update | 20 mins
| delete | 20 mins
4 | backend to DB connection | 5 hrs
5 | Cloud deployment